Carryover of a saddle-node bifurcation paper
https://www.overleaf.com/project/5ec595a5afc7e10001118013
Github repository (private): https://github.com/ccontrer/20-05SNBifurcationCarryover

Wed, Sep 16, 2020
Meeting Gutavo/Gerda/Carlos:
- We are trying Google Room, Github, and overleaf.
- There is going to be a one week delay between paper versions and comments.
- Application section:
  - We might think about a better dynamic for ‘s’, but Gerda thinks it’s fine since this is a proof of concept.
- I will write the second application (cell cycle model) for next week.

Tue, Sep 15, 2020
Logbook:
- I edited the gen activation application python notebook and included info in the readme page.
- I also made the repository public.
- I edited the introduction and application section (first application).

Mon, Sep 14, 2020
Logbook:
I wrote a python notebook for the gen activation application (available on Github)

Wed, Sep 9, 2020 (10 am)
Meeting Gerda, Gustavo and Carlos

Agenda:
- Weekly meetings: Wednesdays 11 am to 1 pm.
- Introduction: refine introduction
- Application: write models (3) and (4). Possibly, the SMB paper and thesis, but if might not worth it.
Gen activation model: parameter to transform into variable. Write application with s into variable instead and decide.

Sep 4, 2020
I worked on the introduction: general case, two applications and more general case. I share the overleaf with Gustavo and Gerda.

Jul 28, 2020 (3-4 pm)

Meeting Gerda, Gustavo and Carlos

Discussion:
- Introduction: start with the general case. Then introduce the two applications, the gen activation model (Strogatz Ex 3.7.5, p.90) and the Tyson’s Cyclin B activation model (Segel Section 12.3 p. 263). Finally, note that we’ll come back to those applications at the end of the paper.
- Application:
  - Gen activation model (Strogatz Ex 3.7.5, p.90): mention that using Meiss’ theorem, the calculation of showing that there is a saddle-node bifurcation is not easy to doa s with our theorems
  - Tyson’s Cyclin B activation model (Segel Section 12.3 p. 263): show numerically both saddle-node bifurcation, in the original and extended.

Jun 8, 2020 (2:30-4 pm)

Meeting Gerda, Gustavo and Carlos

Agenda:
- Carlos is working on the introduction.
- Look at Exercise 3.7.5 on page 90 of the Strogatz’ book, the biochemical switch.
dx/dt=s-rx+ {x} ^ {2} /(1+ {x} ^ {2} )
Either s or r can be turned into a variable. Probably, s makes more sense because it is the signal.

Jun 1, 2020 (2-4 pm)

Meeting Gerda, Gustavo and Carlos

Agenda:
Write Introduction motivation for the next meeting.

May 25, 2020 (2-4 pm)

Meeting Gerda, Gustavo and Carlos

Agenda:
- Possible applications:
  - Strogatz page 243. Parameter a, the inactivation rate of x could be regulated, turning into a parameter.
  - Strogatz page 74. Budworm population dynamics. Ludwig et al. (1978).
  - Logistic equations with saturating harvesting rate [ dN/dt = rN(1-N/K) - H N / (A+N) ]
  - Pendulum equation (I saw something relating it with the saddle-node bifurcation, but I don’t recall it well). It raises when introducing a torque. Can we transform a parameter into a variable?
  - Look at this paper: “Time-Dependent Saddle Node Bifurcation: Breaking Time and thePoint of No Return in a Non-Autonomous Model of CriticalTransitions” Jeremiah H. Li1, Felix X.-F. Ye2, Hong Qian1, and Sui Huang.
  - FitzHugh-Nagumo.
- Papers: it might be more a Differential Equation paper.
- TImeline: Introduction/Applications/Discussion. Deadline: end of August.
- Next actions: start writing the introduction, and look at applications.

May 20, 2020 (2-4 pm)

Meeting Gustavo and Carlos

- Write paper.
- Possible Journals:
Journal of Differential Equations (Elsevier)
Journal of Nonlinear Science (Springer)
SIAM Journal on Applied Mathematics
SIAM Journal on Applied Dynamical Systems
Journal of Dynamics and Differential Equations (Springer)
Differential Equations (Springer)
- It would be great if we find another application. (Look for potential applications).
- Plan for the paper (Saddle-node bifurcation carryover). Discuss with Gerda:
  - Possible Journals and structure of the paper (dictated by the journal).
  - Structure:
    - Introduction: include a motivation for the study of the carryover with a couple of applications including our analysis of the G2/M transition; or simply introduce the theoretical interesting question.
    - Reference to Meiss papers without writing the whole text and Summarize.
    - Include a section of applications: 1) carryover on Novak and Tyson’s model (numerical), 2) carryover on a beautiful and simple application (theoretical).
- Future project: Can the carryover idea be applied to other bifurcations?

May 11, 2020 (3-4 pm)

Meting Gustavo, Carlos.

- To include or not to include the theorems taken from the Meiss [2007]. I think the best idea is to briefly introduce the idea of the theorems (conditions and results) and to refer to the book for details.
- Introductory applications. Perhaps motivate the study of a carryover of a saddle-node bifurcation with our system, the cell cycle model where mass and V_c2 are taken as parameters and they drive a saddle node-de bifurcation. Think about other applications, perhaps the fire and spike neuro model (FitzHugh-Nagumo model)?
- How to introduce Figure 5.6? Or third section: applications from models? Could we cite the paper of the Bulletin of Mathematical Biology to include application in Section 5.3 of the thesis in the paper?